## Sheet1
Epic
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
1 | parents 1 | As a parent, I want to customize a task list and send it to my child, so that I can set it according to the family's specific needs. | high | 1 | Verify the functionality to create a task list within the application. Verify that custom tasks can be added with titles, requirements, labels, and rewards specified for each task. Verify that the task list is correctly displayed in the child's account after it is published. |  | 2024.4.15 | 2024.4.21
2 | parents 2 | As a parent, I want to verify tasks completed by my child and transfer money to their account, so that I can determine if the tasks are completed based on their performance. | high | 1 | Verify that tasks can be verified and marked as completed after the child finishes them. Verify that the corresponding amount is transferred to the child's account upon task completion. Verify that the completed tasks and the corresponding reward amounts are displayed in the child's account. |  | 2024.4.15 | 2024.4.21
3 | parents 3 | As a parent, I want to provide both savings and current account options, so that my child can manage money in different ways. | high | 1 | Verify that the application provides options for both savings and current accounts. Verify that a specific amount can be chosen for savings deposits. Verify that the deposited amount is correctly displayed in the child's account after a successful deposit. |  | 2024.4.15 | 2024.4.21
4 | parents 4 | As a parent, I want to offer various financial products for my child to choose from, so that I can cultivate their understanding of different profitable products. | medium | 2 | Verify that the application provides different types of financial products, such as savings accounts with different interest rates. Verify that relevant information, such as interest rates and minimum deposit amounts, is displayed for each financial product. Verify that the child can select and open the chosen financial product. Verify that the child's account correctly displays the selected financial product and its relevant information. |  | 2024.4.22 | 2024.4.28
5 | parents 5 | As a parent, I want my child to be able to use the money in their account to redeem rewards from me, so that I can motivate them further. | medium | 2 | Verify that the available balance is displayed in the child's account. Verify that the corresponding amount is deducted from the child's account when they redeem the money and record the redemption details. Verify that the redemption details are correctly displayed in the transaction history. |  | 2024.4.22 | 2024.4.28
6 | parents 6 | As a parent, I want to view my child's transaction details and financial statements, so that I can understand their financial behavior. | medium | 2 | Verify that the application provides the functionality to view the child's transaction details and financial statements. Verify that the transaction details include records of deposits, withdrawals, and reward redemptions. Verify that the financial statement displays the financial products chosen by the child, relevant information, and earnings. |  | 2024.4.22 | 2024.4.28
7 | parents 7 | As a parent, I want to access a parental control interface with a password, so that I can prevent the child from setting tasks themselves. | medium | 2 | Verify that the application provides the functionality to set a parental password. Verify that only the correct parental password allows access to the parental control interface. Verify that the child's account does not have the authority to set tasks and can only perform tasks set by the parent. |  | 2024.4.22 | 2024.4.28
8 | child 1 | As a child, I want to have the freedom to choose different money-earning tasks, so that I can do tasks that I prefer. | high | 1 | Verify that a task list exists in the interface, displaying available money-earning tasks. Verify that the child can browse the task list and view the task's title, description, and reward. Verify that the child can select and accept tasks. Verify that the corresponding reward amount is correctly displayed in the child's account after completing the task. |  | 2024.4.15 | 2024.4.21
9 | child 2 | As a child, I want a more diverse way of saving money, so I can choose the method that suits me based on the actual situation. | high | 1 | Verify that the application provides multiple saving methods, such as current deposit and fixed deposit. Verify that the correct amount is displayed in the child's account after a successful deposit. |  | 2024.4.15 | 2024.4.21
10 | child 3 | As a child, I want a cute and simple banking interface, so I can focus and use the system more quickly and conveniently. | medium | 2 | Verify that the application interface design appeals to children and adopts a cute and simple style. Verify that the interface layout is clear, and functional buttons are easy to identify and operate. Verify that the interface loads quickly, responds promptly, and provides a faster and more convenient user experience. |  | 2024.4.22 | 2024.4.28
11 | child 4 | As a child, I want to try financial products with higher profits, so I can increase my savings. | medium | 2 | Verify that the application provides financial products with different profits. Verify that each financial product displays relevant information such as interest rate, risk level, minimum deposit amount, and fixed term. |  | 2024.4.22 | 2024.4.28
12 | child 5 | As a child, I want the software to include some banking-related knowledge, so I can understand the concept and usage of banking. | low | 3 | Verify that the knowledge base includes basic concepts of banking, depositing, withdrawing, interest rates, and other relevant content. Verify that children can browse and learn from the content in the knowledge base. |  | 2024.4.29 | 2024.5.1